## Gantt Chart (weeks)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | June |  |  | July |  |  |  |  | August
[5 empty] | 10/Jun - 16/Jun | 17/Jun - 23/Jun | 24/Jun - 30/Jun | 01/Jul - 07/Jul | 08/Jul - 14/Jul | 15/Jul - 21/Jul | 22/Jul - 28/Jul | 29/Jul - 04/Aug | 05/Aug - 11/Aug | 12/Aug - 18/Aug | 19/Aug - 25/Aug
Task 1 | Understanding Client Requirements | 10-Jun-2024 | 16-Jun-2024 | High
1.1 | Meet with the client to understand the business logic and requirements | 10-Jun-2024 | 16-Jun-2024 | High
Task 2 | Database Design and Setup | 17-Jun-2024 | 23-Jun-2024 | Medium
2.1 | Design SQL tables and establish relationships with primary keys | 17-Jun-2024 | 23-Jun-2024 | Medium
2.2 | Build the database structure | 17-Jun-2024 | 23-Jun-2024 | Medium
Task 3 | Connecting Database to Application | 24-Jun-2024 | 30-Jun-2024 | High
3.1 | Use Entity Framework to connect the database to the .NET solution | 24-Jun-2024 | 30-Jun-2024 | High
3.2 | Create models reflecting the database schema | 24-Jun-2024 | 30-Jun-2024 | High
Task 4 | Setting Up Data Access Layer | 01-Jul-2024 | 07-Jul-2024 | Low
4.1 | Create repositories and configure models for data access | 01-Jul-2024 | 07-Jul-2024 | Low
Task 5 | Implementing Business Logic Layer | 08-Jul-2024 | 14-Jul-2024 | High
5.1 | Define interfaces and implement services to handle business logic | 08-Jul-2024 | 14-Jul-2024 | High
Task 6 | Developing the User Interface | 15-Jul-2024 | 04-Aug-2024 | Medium
6.1 | Create the views for user interactions | 15-Jul-2024 | 21-Jul-2024 | Medium
6.2 | Add dynamic features (JavaScript) | 15-Jul-2024 | 28-Jul-2024 | Medium
6.3 | Add dynamic features (JAJAX) | 22-Jul-2024 | 28-Jul-2024 | Medium
6.4 | Add dynamic features (Modals) | 22-Jul-2024 | 28-Jul-2024 | Medium
6.5 | Add dynamic features (offcanvas) | 22-Jul-2024 | 28-Jul-2024 | Medium
6.6 | Customize the style of the page | 29-Jul-2024 | 04-Aug-2024 | Medium
6.7 | Revising the CSS scripts and Bootstrap libraries | 29-Jul-2024 | 04-Aug-2024 | Medium
Task 7 | Controllers and Backend Integration | 05-Aug-2024 | 18-Aug-2024 | Low
7.1 | Develop controllers to manage actions and data flow | 05-Aug-2024 | 11-Aug-2024 | Low
7.2 | Implement async tasks and handle responses | 05-Aug-2024 | 18-Aug-2024 | Low
Task 8 | Testing and Validation | 19-Aug-2024 | 25-Aug-2024 | High
8.1 | Create customized examples for testing | 19-Aug-2024 | 25-Aug-2024 | High
8.2 | Test for various scenarios to ensure functionality | 19-Aug-2024 | 25-Aug-2024 | High
8.3 | Facilitate user testing to validate the application with real users | 19-Aug-2024 | 25-Aug-2024 | High

## Gantt Chart (months)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | June |  |  | July |  |  |  |  | August
[5 empty] | 10/Jun - 16/Jun | 17/Jun - 23/Jun | 24/Jun - 30/Jun | 01/Jul - 07/Jul | 08/Jul - 14/Jul | 15/Jul - 21/Jul | 22/Jul - 28/Jul | 29/Jul - 04/Aug | 05/Aug - 11/Aug | 12/Aug - 18/Aug | 19/Aug - 25/Aug
Task 1 | Understanding Client Requirements | 10-Jun-2024 | 16-Jun-2024 | High
Task 2 | Database Design and Setup | 17-Jun-2024 | 23-Jun-2024 | Medium
Task 3 | Connecting Database to Application | 24-Jun-2024 | 30-Jun-2024 | High
Task 4 | Setting Up Data Access Layer | 01-Jul-2024 | 07-Jul-2024 | Low
Task 5 | Implementing Business Logic Layer | 08-Jul-2024 | 14-Jul-2024 | High
Task 6 | Developing the User Interface | 15-Jul-2024 | 04-Aug-2024 | Medium
Task 7 | Controllers and Backend Integration | 05-Aug-2024 | 18-Aug-2024 | Low
Task 8 | Testing and Validation | 19-Aug-2024 | 25-Aug-2024 | High

## Project Schedule
Tasks | Activity | Start Date | End Date | Status | Complete
Task 1 | Understanding Client Requirements | 10-Jun-2024 | 16-Jun-2024 | Ongoing | 100%
1.1 | Meet with the client to understand the business logic and requirements | 10-Jun-2024 | 16-Jun-2024 | Ongoing | 100%
Task 2 | Database Design and Setup | 17-Jun-2024 | 23-Jun-2024 | Ongoing | 100%
2.1 | Design SQL tables and establish relationships with primary keys | 17-Jun-2024 | 23-Jun-2024 | Ongoing | 100%
2.2 | Build the database structure | 17-Jun-2024 | 23-Jun-2024 | Ongoing | 100%
Task 3 | Connecting Database to Application | 24-Jun-2024 | 30-Jun-2024 | Ongoing | 100%
3.1 | Use Entity Framework to connect the database to the .NET solution | 24-Jun-2024 | 30-Jun-2024 | Ongoing | 100%
3.2 | Create models reflecting the database schema | 24-Jun-2024 | 30-Jun-2024 | Ongoing | 100%
Task 4 | Setting Up Data Access Layer | 01-Jul-2024 | 07-Jul-2024 | Ongoing | 100%
4.1 | Create repositories and configure models for data access | 01-Jul-2024 | 07-Jul-2024 | Ongoing | 100%
Task 5 | Implementing Business Logic Layer | 08-Jul-2024 | 14-Jul-2024 | Ongoing | 100%
5.1 | Define interfaces and implement services to handle business logic | 08-Jul-2024 | 14-Jul-2024 | Ongoing | 100%
Task 6 | Developing the User Interface | 15-Jul-2024 | 04-Aug-2024 | Ongoing | 100%
6.1 | Create the views for user interactions | 15-Jul-2024 | 21-Jul-2024 | Ongoing | 100%
6.2 | Add dynamic features (JavaScript | 15-Jul-2024 | 28-Jul-2024 | Ongoing | 100%
6.3 | AJAX | 22-Jul-2024 | 28-Jul-2024 | Ongoing | 100%
6.4 | modals | 22-Jul-2024 | 28-Jul-2024 | Ongoing | 100%
6.5 | offcanvas) to the views | 22-Jul-2024 | 28-Jul-2024 | Ongoing | 100%
6.6 | Customize the style of the page | 29-Jul-2024 | 04-Aug-2024 | Ongoing | 100%
6.7 | revising the CSS scripts and Bootstrap libraries | 29-Jul-2024 | 04-Aug-2024 | Ongoing | 100%
Task 7 | Controllers and Backend Integration | 05-Aug-2024 | 18-Aug-2024 | Ongoing | 100%
7.1 | Develop controllers to manage actions and data flow | 05-Aug-2024 | 11-Aug-2024 | Ongoing | 100%
7.2 | Implement async tasks and handle responses | 05-Aug-2024 | 18-Aug-2024 | Ongoing | 100%
Task 8 | Testing and Validation | 19-Aug-2024 | 25-Aug-2024 | Ongoing | 100%
8.1 | Create customized examples for testing | 19-Aug-2024 | 25-Aug-2024 | Ongoing | 100%
8.2 | Test for various scenarios to ensure functionality | 19-Aug-2024 | 25-Aug-2024 | Ongoing | 100%
8.3 | Facilitate user testing to validate the application with real users | 19-Aug-2024 | 25-Aug-2024 | Ongoing | 100%